## Features
Project: LogBlock
Team: 5
Testing Items
ID | Feature Name | Description | Remark
T01 | Front-End Authorization | Element displaying and page access should consider the User's authorization to display correctly. | Front-End authorization component before rendering of each Page
T02 | Data Access correctness | Unit testing of Database and Back-End integration. Full entity (row) retrieval and insertion into each repository (table) correctness checking. | 3 cases of data insertion and 3 cases of data retrieval for each Entity
T03 | Controllers Unit testing | Controllers should be able to access required Services | Each controllers should be tested for function handling of logic processing and null or unexpected exception
T04 | News Feed Generation correctness | Testing for expected behaviour of the News Feed Generation Use Case | Testing for Users of different connections states and feeds generation correctness by checking retrieved post id
T03 | Profile, Posting and Comment interaction correctness | Controllers should be able to access required Services | Each controllers should be tested for function handling of logic processing and null or unexpected exception

## Test cases
Function/Feature ID | Case ID | Test case name | Test step | Expected Result (ER) | Actual Result | Status | Tester | Tested Date | Remark
Function 01: Front-end Authorization
T01 | TI01 | Guest User Login Page | 1. Go to the website without signing in | 1. The login page is displayed for the user | Same ER | Pass | NTTLong | 2024-12-25
| TI02 | Main Page for Signed in user | 1. Login to the server | 1. The news feed for the user is generated, as well as the UI to other elements of the application. | The News Feed UI does not match the design closely | Pass | NTTLong | 2024-12-25
| TI03 | Profile Page for Signed in user | 1. Login to the server 2. Press the profile icon to access profile page | 1. The profile of the user is displayed | Same ER | Pass | NTTLong | 2024-12-25
| TI04 | ESS for Expert User | 1. Login to the server as an Expert User 2. Click on More options button of a comment | 1. The option for proposing an ESS is displayed | ESS UI is not yet implemented | Fail | NTTLong | 2024-12-25
| TI05 | Reports Review for Administrator | 1. Login to the server as an Administrator 2. Press on | 1. The Report Page navigator should be displayed 2. The Report page should be rendered correctly | Same ER | Pass | NTTLong | 2024-12-25
Function 02: Data Access correctness
T02 | TI01 | Insertion standard profile | 1. Create a new account with emails "johndoe@mail.com" and "willsmith@mail.com". 2. Update display name, biography, profile image, and privilege level for each account. 3. Check if the user profiles are correctly inserted in the database. | User profiles are created and updated correctly with the following data: - Display name, biography description, profile image, and privilege level are accurately stored. - User data retrieved matches the input data. | Same ER | Pass | TCAn | 2024-12-25
| TI02 | Create Connection | 1. Create a valid ConnectionDTO object with connector ID and connected ID. 2. Call the createConnection method. 3. Verify that the connection was created and saved in the database. | 1. The method createConnection should return 1 indicating success. 2. The connection should be saved in the database. 3. The created connection should match the provided connector and connected IDs. | Same ER | Pass | TCAn | 2024-12-25
| TI03 | Delete Connection | 1. Create a connection using valid IDs. 2. Call the deleteConnection method. 3. Verify that the connection is deleted from the database. | 1. The method deleteConnection should return 1 indicating success. 2. The connection should be removed from the database and no longer exist in the list of connections. | Same ER | Pass | TCAn | 2024-12-25
| TI04 | Create Report | 1. Create a user profile. 2. Create a valid ReportingDTO object with report details. 3. Call the createReport method. 4. Verify that the report is created and saved in the database. | 1. The method createReport should return a valid report ID. 2. The report should be saved in the database and its details (reporterID and reportedPostID) should match the provided data. | Same ER | Pass | TCAn | 2024-12-25
| TI05 | Retrieve Report Info | 1. Create a user profile. 2. Create a valid ReportingDTO object and create the report. 3. Retrieve the report by ID. 4. Verify that the retrieved report matches the expected values. | 1. The retrieved report should not be null. 2. The report details (reportID, reporterID, reportedPostID) should match the values used when creating the report. | Same ER | Pass | TCAn | 2024-12-25
| TI06 | Delete Report | 1. Create a user profile. 2. Create a valid ReportingDTO object and create the report. 3. Call the deleteReport method. 4. Verify that the report is deleted from the database. | 1. The method deleteReport should return 1, indicating successful deletion. 2. The report should no longer exist in the database. | Same ER | Pass | TCAn | 2024-12-25
| TI07 | Delete Non-Existing Report | 1. Call the deleteReport method with a non-existing report ID. 2. Verify that the deletion attempt fails. | 1. The method deleteReport should return 0, indicating failure to delete a non-existing report. | Same ER | Pass | TCAn | 2024-12-25
| TI08 | Create Post | 1. Create a new user profile. 2. Create several PostingDTO objects with valid data (userID and caption). 3. Call the createPost method to insert posts. 4. Verify that the number of posts in the database matches the number of posts created. 5. Verify that the post data (authorID and caption) in the database matches the provided data. | 1. The number of posts in the database should match the number of test inputs. 2. Each post should have the correct authorID and caption as specified in the test inputs. | Same ER | Pass | NKHung | 2024-12-25
| TI09 | Retrieve Post by ID | 1. Create a user profile. 2. Create a post. 3. Retrieve the post using the generated post ID. 4. Verify that the retrieved post is not null. 5. Verify that the post's authorID and caption match the expected values. | 1. The retrieved post should not be null. 2. The authorID and caption of the retrieved post should match the values used when creating the post. | Same ER | Pass | NKHung | 2024-12-25
| TI10 | Create ESS | 1. Set up a mock ExpertSuggestedSolution object. 2. Create a testESSDTO for the solution. 3. Mock the repository's addESS method to return a valid ESS ID. 4. Call createESS method on the service. 5. Verify that the returned ESS ID matches the expected one. | 1. The method should return the correct ESS ID matching the one created in the test. | Same ER | Pass | TCAn | 2024-12-25
| TI11 | Get ESS by ID | 1. Mock the repository's findById method to return a valid ExpertSuggestedSolution. 2. Call getESS method on the service. 3. Verify that the returned ESS matches the expected values. | 1. The service should return a valid ESS with the correct solution ID, and it should match the expected values. 2. The result should be present and not null. | Same ER | Pass | TCAn | 2024-12-25
| TI12 | Update ESS | 1. Set up a mock ExpertSuggestedSolution object to update. 2. Mock the repository's updateESS method to return a valid ESS ID. 3. Call updateESS on the service. 4. Verify the returned ESS ID is the same as the updated ESS ID. | 1. The method should return the updated ESS ID. 2. The ESS ID should match the one provided in the test. | Same ER | Pass | TCAn | 2024-12-25
| TI13 | Delete ESS | 1. Mock the repository's removeESS method to return 1 (successful deletion). 2. Call deleteESS on the service. 3. Verify that the method returns 1 indicating successful deletion. | 1. The method should return 1, indicating that the deletion was successful. 2. The ESS should be deleted from the repository. | Same ER | Pass | TCAn | 2024-12-25
| TI14 | Delete ESS (Not Found) | 1. Mock the repository's removeESS method to return 0 (ESS not found). 2. Call deleteESS on the service. 3. Verify that the method returns 0 indicating that the ESS was not found and could not be deleted. | 1. The method should return 0, indicating that the ESS was not found and thus could not be deleted. | Same ER | Pass | TCAn | 2024-12-25
| TI15 | Create Comment | 1. Set up the initial comment object. 2. Mock the addCommenting repository method to return the correct comment ID. 3. Call createComment on the service. 4. Verify the correct return value and repository interaction. | 1. The service should return the correct comment ID (1 in this case). 2. The addCommenting method should be called once with the correct parameters. | Same ER | Pass | TNNCuong | 2024-12-25
| TI16 | Update Comment | 1. Set up the updated comment object. 2. Mock the updateCommenting repository method to return the updated comment ID. 3. Call updateComment on the service. 4. Verify the correct return value and repository interaction. | 1. The service should return the updated comment ID. 2. The updateCommenting method should be called once with the correct parameters. | Same ER | Pass | TNNCuong | 2024-12-25
| TI17 | Get Comment | 1. Mock the repository's findById method to return an existing comment. 2. Call getComment on the service. 3. Verify that the returned comment matches the expected values. | 1. The service should return a Commenting object wrapped in Optional. 2. The Commenting object should have the correct caption and values from the original comment. | Same ER | Pass | TNNCuong | 2024-12-25
| TI18 | Delete Comment | 1. Mock the repository's removeCommenting method to return 1 (successful deletion). 2. Call deleteComment on the service. 3. Verify the correct return value and repository interaction. | 1. The service should return 1, indicating successful deletion. 2. The removeCommenting method should be called once with the correct parameters. | Same ER | Pass | TNNCuong | 2024-12-25
| TI19 | Update Non-Existing Comment | 1. Set up an updated comment object. 2. Mock the repository's updateCommenting method to return -1 (non-existing comment). 3. Call updateComment on the service. 4. Verify the correct return value. | 1. The service should return -1, indicating that the comment could not be updated because it doesn’t exist. | Same ER | Pass | TNNCuong | 2024-12-25
| TI20 | Delete Non-Existing Comment | 1. Mock the repository's removeCommenting method to return 0 (comment not found). 2. Call deleteComment on the service. 3. Verify the correct return value. | 1. The service should return 0, indicating that the comment could not be deleted because it doesn’t exist. | Same ER | Pass | TNNCuong | 2024-12-25
| TI21 | Retrieve All Reports | 1. Set up sample Reporting data. 2. Mock findAllReports method to return a list of reports. 3. Call retrieveAllReports on the service. 4. Verify that the list size is 2 and the first two report IDs match. | 1. The service should return a list of reports of size 2. 2. The reported post IDs should match the expected values (101 and 102). | Same ER | Pass | TCAn | 2024-12-25
| TI22 | Remove Post | 1. Mock removePost to return 1 (successful deletion). 2. Call removePost on the service. 3. Verify that the result is 1 and the method was called once. | 1. The service should return 1 for successful post deletion. 2. The removePost method should be called once. | Same ER | Pass | TCAn | 2024-12-25
| TI23 | Remove Post Not Found | 1. Mock removePost to return 0 (post not found). 2. Call removePost on the service. 3. Verify that the result is 0 and the method was called once. | 1. The service should return 0 when the post is not found. 2. The removePost method should be called once. | Same ER | Pass | TCAn | 2024-12-25
| TI24 | Close Account | 1. Mock deleteAccount in AccountService to return 1 (successful closure). 2. Call closeAccount on the service. 3. Verify that the result is 1 and the method was called once. | 1. The service should return 1 for successful account closure. 2. The deleteAccount method should be called once. | Same ER | Pass | NKHung | 2024-12-25
| TI25 | Close Account Not Found | 1. Mock deleteAccount in AccountService to return 0 (account not found). 2. Call closeAccount on the service. 3. Verify that the result is 0 and the method was called once. | 1. The service should return 0 when the account is not found. 2. The deleteAccount method should be called once. | Same ER | Pass | NKHung | 2024-12-25
Function 03: Controllers Unit testing
T03 | TI01 | Retrieve information of a user | 1. Send GET request /profiles/{userID} with userID is available | 1. The information of the user is return 2. The HTTP code is 200 | Same ER | Pass | TTLong | 2024-12-25
| TI02 | Retrieve information from a non-existing user | 1. Send GET request /profiles/{userID} with userID is not available | 1. Nothing is return 2. The HTTP code is 404 | The return HTTP code is 204 due to incorrect implementation | Fail | TTLong | 2024-12-25
| TI03 | Retrieve information of a post | 1. Send GET request /posts/{postID} with postID is available | 1. The information of the post is return 2. The HTTP code is 200 | Same ER | Pass | TTLong | 2024-12-25
| TI04 | Retrieve information from a non-existing post | 1. Send GET request /posts/{postD} with postID is not available | 1. Nothing is return 2. The HTTP code is 404 | The return HTTP code is 204 due to incorrect implementation | Fail | TTLong | 2024-12-25
| TI05 | Retrieve information of a comment | 1. Send GET request /comments/{postID}/{commentID} with postID and commentID is available | 1. The information of the comment is return 2. The HTTP code is 200 | Same ER | Pass | TTLong | 2024-12-25
| TI06 | Retrieve information when not authorized | 1. Send GET request without login into the server | 1. The HTTP code is 403 | Same ER | Pass | TTLong | 2024-12-25
Function 04: News Feed Generation correctness
T04 | TI01 | Generate Feed With Valid Connections | 1. Create mock data for connections and posts. 2. Mock findByConnectorID to return connections. 3. Mock findPostingsByUserID to return posts. 4. Call generate method. 5. Assert the returned posts match expected posts. | 1. The service should return 2 posts. 2. The captions of the posts should match "Post by User 2" and "Post by User 3". 3. Verify interactions with repositories. | Same ER | Pass | TCan | 2024-12-26
| TI02 | Generate Feed With No Connections | 1. Mock findByConnectorID to return an empty list. 2. Call generate method. 3. Assert the result is an empty list. 4. Verify postRepository is not interacted with. | 1. The service should return an empty list. 2. postRepository should not be interacted with. | Same ER | Pass | TCan | 2024-12-26
| TI03 | Generate Feed With Empty Posts | 1. Create mock data for connections but no posts. 2. Mock findPostingsByUserID to return an empty list. 3. Call generate method. 4. Assert the result is an empty list. 5. Verify interactions with repositories. | 1. The service should return an empty list. 2. Verify that findByConnectorID and findPostingsByUserID are called once. | Same ER | Pass | TCan | 2024-12-26
| TI04 | Generate Feed With Null Connections | 1. Mock findByConnectorID to return null. 2. Call generate method. 3. Assert the result is not null and is an empty list. 4. Verify that no interactions occurred with postRepository. | 1. The result should not be null. 2. The result should be an empty list when connections is null. 3. Verify that postRepository is not interacted with. | Same ER | Pass | TNNCuong | 2024-12-26
| TI05 | Generate Trending Feed With Posts | 1. Create mock data for trending posts. 2. Mock findTrendingPosts to return the trending posts. 3. Call generate method. 4. Assert that the size of the result matches expected. 5. Assert that the post captions are correct. | 1. The result should contain 2 posts. 2. The captions should be "Trending Post 1" and "Trending Post 2". 3. Ensure that findTrendingPosts was called once. | Same ER | Pass | TNNCuong | 2024-12-26
| TI06 | Generate Trending Feed With No Posts | 1. Mock findTrendingPosts to return an empty list. 2. Call generate method. 3. Assert that the result is an empty list. 4. Ensure that findTrendingPosts was called once. | 1. The result should be an empty list. 2. Ensure that findTrendingPosts was called once. | Same ER | Pass | TNNCuong | 2024-12-26
Function 05: Profile, Posting and Comment interaction correctness
T05 | TI01 | Creating Text-only Posting | 1. Access the system SPA 2. Authenticate through OAuth2.0 3. Landing at the root of the SPA, click on the "What are you thinking?" box 4. Enters an arbitrary caption. 5. Use the Create button | 1. The post content should be visible in the News Feed 2. The post content should be visible in the Profile Feed 3. The post should contain the correct caption | Same ER | Pass | NKHung | 2024-12-26
| TI02 | Creating standard posting | 1. Access the system SPA 2. Authenticate through OAuth2.0 3. Landing at the root of the SPA, click on the "What are you thinking?" box 4. Enters an arbitrary caption 5. Enter an image through local uploading 6. Use the Create button | 1. The post content should be visible in the News Feed 2. The post content should be visible in the Profile Feed 3. The post should contain the correct caption 4. The post should contain the uploaded image | Same ER | Pass | NKHung | 2024-12-26
| TI03 | Posting autoloader functional testing | 1. Access the system SPA 2. Authenticate through OAuth2.0 3. Insert 10 arbritrary posts through standard posting 4. Reload the page, keep scrolling down to load new posts | 1. The inserted post should all be displayed correctly 2. The post should be in the same order as the insertion 3. The system should automatically load new post when the user hit the end of the page 4. No duplication of posts | The posts displayed at arbitrary order. Autoloader requires scrolling down furthur than other applications | Fail | NKHung | 2024-12-26
| TI04 | Commenting | 1. Access the system SPA 2. Authenticate through OAuth2.0 3. Create an arbritrary post 4. Click on the bubble icon in the recently created post 5. Type in the comment caption box 6. Press enter | 1. The comment should appear on the post 2. Upon reloading of the post element, comments should also be present 3. The comment should have the same content as the input 4. The comment should appear in order | The comment sometimes appear in random order. The comment cannot renders the author's profile image. The UI is not very user friendly, showing more comment should be at the end of the post | Fail | NKHung | 2024-12-26
| TI05 | Profile | 1. Access the system SPA 2. Authenticate through OAuth2.0 using many Google Account (3) 3. Go to the Profile Page by using the third icon from top down at the leftside navigation bar 4. Save the Profile URL 5. On each account, create 1-2 arbitrary postings. 6. Using a 4th account, visit the URL of each of the three accounts | 1. The profiles URLs must exists 2. The profiles content as well as the posts content should be correct. 3. The profile page should also supports autoloading | Adding comment to the post at other location ther than this page could cause a non-crashing error in the Back end system | Fail | NKHung | 2024-12-26